## Sheet1 (hidden)
S.No | WPS Category & Sub Category | Urportal | New Features
1 | Organisation Profile
2 | Profile Status | Done
3 | Employees according to RTI | Done
4 | Authorizing officer | Done
5 | Key Contact | Done
6 | Level 1 user | Done
7 | Organisation | Done
8 | Organisation profile | Processing
9 | Employees Creation Link | Processing
10 | Settings
11 | HCM Master
12 | Department | Done
13 | Designation | Done
14 | Employment Type | Done
15 | Pay group | Processing
16 | Annual Pay | Processing
17 | Bank Master | Processing
18 | Bank Sortcode | Processing
19 | Tax Master | Processing
20 | Payment Type | Processing
21 | Wedges Pay mode | Processing
22 | Payroll | Processing
23 | Pay Item | Processing
24 | Recruitment
25 | Job List | Done
26 | Job Posting | Done
27 | Job published | Done
28 | Job Applied
29 | Short Listing
30 | Interview
31 | Hired
32 | Generate offer letter
33 | Search
34 | Status search
35 | Rejected
36 | Message Centre | Done
37 | Mock Interview
38 | Employee | Done
39 | Change of circumstances | Done
40 | Add | Done
41 | View | Done
42 | Contract Agreement | Done
43 | User Access | Done
44 | Role Managememt | Done
45 | User Configuration | Done
46 | Role Managememt | Done
47 | Organogram Chart | Done
48 | Level 1 | Done
49 | Organisation Hierarchy | Done
50 | Holiday Management
51 | Holiday Type
52 | Holiday List
53 | Leave Management
54 | Manage Leave Type
55 | Leave Rule
56 | Leave Allocation
57 | Leave Balance
58 | Leave Report
59 | Leave Report Employee Wise
60 | Rota
61 | Time Shift Management
62 | Shift Managemet
63 | Late Policy
64 | Day off
65 | Grace Period
66 | Duty Roster
67 | Visitor
68 | Visitor Register Link
69 | Visitor Register
70 | Attendance
71 | Attendance Management
72 | Upload Attendance
73 | Generate Attendance
74 | Daily Attendance
75 | Attendance History
76 | Process Attendance
77 | Absent Report
78 | Leave Approver
79 | Approver Corner
80 | Leave Request List
81 | Payroll
82 | Billing
83 | Billing
84 | Payment Receipt
85 | Documents
86 | Staff Report
87 | Archive
88 | Organisation Report
89 | Employee Report
90 | Employee Archive Report
91 | Sponsor Compliance
92 | organisation Profile | Working on
93 | All Employee List | Done
94 | Migrant Employee List
95 | Right to work checks
96 | Recruitment Process
97 | Leave Management
98 | Payroll
99 | Key Contact | Done
100 | Sponsor Management Dossier
101 | Monitoring & Reporting
102 | Message Centre | Done
103 | Staff Report
104 | Absent Report
105 | Change of circumstances
106 | Contract Agreement
107 | Visa Notification
108 | Passport Notrification
109 | DBS Notification
110 | EUSS notification
111 | Right to work
112 | Employee Corner
113 | Sign in to Employee Account
114 | Tasks | Done

## Software Dateline
1 | Organisation Profile | Status | Comments | Not Done List
2 | Profile Status | Done |  | SL | Description | Status | ApproximatelyDays | Approximately Date
3 | Employees according to RTI | Done |  | 1 | Organisation Profile
4 | Authorizing officer | Done |  |  | Organisation profile | Done | 2 Days | 28-08-2023 to 30-08-2023
5 | Key Contact | Done |  |  | Employees Creation Link | Done
6 | Level 1 user | Done
7 | Organisation | Done |  | 2 | Setting Module
8 | Organisation profile | Processing |  |  | Pay group | Done | 4 Days | 31-08-2023 to 04-09-2023
9 | Employees Creation Link | Processing |  |  | Annual Pay | Done
10 | Settings |  |  |  | Bank Master | Done
11 | HCM Master |  |  |  | Bank Sortcode | Done
12 | Department | Done |  |  | Tax Master | Done
13 | Designation | Done |  |  | Payment Type | Done
14 | Employment Type | Done |  |  | Wedges Pay mode | Done
15 | Pay group | Processing |  |  | Payroll | Done
16 | Annual Pay | Processing |  |  | Pay Item | Done
17 | Bank Master | Processing
18 | Bank Sortcode | Processing |  | 3 | Recruitment Module
19 | Tax Master | Processing |  |  | Job Applied | Done | 5 Days | 04-09-2023 to 09-09-2023
20 | Payment Type | Processing |  |  | Short Listing | Done
21 | Wedges Pay mode | Processing |  |  | Interview | Done
22 | Payroll | Processing |  |  | Hired | Done
23 | Pay Item | Processing |  |  | Generate offer letter | Done
24 | Recruitment |  |  |  | Search | Done
25 | Job List | Done |  |  | Status search | Done
26 | Job Posting | Done |  |  | Rejected | Done
27 | Job published | Done
28 | Job Applied |  |  | 3 | Holiday Management Module
29 | Short Listing |  |  |  | Holiday Type | Not done | 2 Days | 10-09-2023 to 12-09-2023
30 | Interview |  |  |  | Holiday List | Not done
31 | Hired
32 | Generate offer letter |  |  | 4 | Leave Management Module
33 | Search |  |  |  | Manage Leave Type | Not done | 3 Days | 13-09-2023 to 16-09-2023
34 | Status search |  |  |  | Leave Rule | Not done
35 | Rejected |  |  |  | Leave Allocation | Not done
36 | Message Centre | Done |  |  | Leave Balance | Not done
37 | Mock Interview |  |  |  | Leave Report | Not done
38 | Employee | Done |  |  | Leave Report Employee Wise | Not done
39 | Change of circumstances | Done
40 | Add | Done |  | 4 | Rota Module
41 | View | Done |  |  | Time Shift Management | Not done | 5 Days | 17-09-2023 to 22-09-2023
42 | Contract Agreement | Done |  |  | Shift Managemet | Not done
43 | User Access | Done |  |  | Late Policy | Not done
44 | Role Managememt | Done |  |  | Day off | Not done
45 | User Configuration | Done |  |  | Grace Period | Not done
46 | Role Managememt | Done |  |  | Duty Roster | Not done
47 | Organogram Chart | Done |  |  | Visitor | Not done
48 | Level 1 | Done |  |  | Visitor Register Link | Not done
49 | Organisation Hierarchy | Done |  |  | Visitor Register | Not done
50 | Holiday Management | Processing
51 | Holiday Type | Processing |  | 6 | Attendance Module
52 | Holiday List | Processing |  |  | Attendance Management | Not done | 3 Days | 23-09-2023 to 24-09-2023
53 | Leave Management | Processing |  |  | Upload Attendance | Not done
54 | Manage Leave Type | Processing |  |  | Generate Attendance | Not done
55 | Leave Rule | Processing |  |  | Daily Attendance | Not done
56 | Leave Allocation | Processing |  |  | Attendance History | Not done
57 | Leave Balance | Processing |  |  | Process Attendance | Not done
58 | Leave Report | Processing |  |  | Absent Report | Not done
59 | Leave Report Employee Wise
60 | Rota |  |  | 7 | Payroll Module
61 | Time Shift Management |  |  | 8 | Billing Module
62 | Shift Managemet
63 | Late Policy |  |  | 9 | Documents Module
64 | Day off |  |  |  | Staff Report | Not done | 3 Days | 25-09-2023 to 28-09-2023
65 | Grace Period |  |  |  | Archive | Not done
66 | Duty Roster |  |  |  | Organisation Report | Not done
67 | Visitor |  |  |  | Employee Report | Not done
68 | Visitor Register Link |  |  |  | Employee Archive Report | Not done
69 | Visitor Register
70 | Attendance |  |  | 10 | Sponsor Compliance
71 | Attendance Management |  |  |  | Migrant Employee List | Not done | 5 Days | 29-09-2023 to 04-10-2023
72 | Upload Attendance |  |  |  | Right to work checks | Not done
73 | Generate Attendance |  |  |  | Recruitment Process | Not done
74 | Daily Attendance |  |  |  | Leave Management | Not done
75 | Attendance History |  |  |  | Payroll | Not done
76 | Process Attendance |  |  |  | Sponsor Management Dossier | Not done
77 | Absent Report |  |  |  | Monitoring & Reporting | Not done
78 | Leave Approver |  |  |  | Staff Report | Not done
79 | Approver Corner |  |  |  | Absent Report | Not done
80 | Leave Request List |  |  |  | Change of circumstances | Not done
81 | Payroll |  |  |  | Contract Agreement | Not done
82 | Billing |  |  |  | Visa Notification | Not done
83 | Billing |  |  |  | Passport Notrification | Not done
84 | Payment Receipt |  |  |  | DBS Notification | Not done
85 | Documents |  |  |  | EUSS notification | Not done
86 | Staff Report |  |  |  | Right to work | Not done
87 | Archive
88 | Organisation Report |  |  | 11 | Employee Corner
89 | Employee Report |  |  |  | Sign in to Employee Account | Not done | 5 Days | 05-10-2023 to 10-10-2023
90 | Employee Archive Report |  |  |  | Absent Report | Not done
91 | Sponsor Compliance |  |  |  | Change of circumstances | Not done
92 | organisation Profile | Working on |  |  | Contract Agreement | Not done
93 | All Employee List | Done |  |  | Visa Notification | Not done
94 | Migrant Employee List |  |  |  | Passport Notrification | Not done
95 | Right to work checks |  |  |  | DBS Notification | Not done
96 | Recruitment Process |  |  |  | EUSS notification | Not done
97 | Leave Management |  |  |  | Right to work | Not done
98 | Payroll
99 | Key Contact | Done |  | 11 | Employee Corner
100 | Sponsor Management Dossier |  |  |  | Sign in to Employee Account | Not done | 10 Days | 10-10-2023 to 20-10-2023
101 | Monitoring & Reporting
102 | Message Centre | Done
103 | Staff Report
104 | Absent Report
105 | Change of circumstances
106 | Contract Agreement
107 | Visa Notification
108 | Passport Notrification
109 | DBS Notification
110 | EUSS notification
111 | Right to work
112 | Employee Corner
113 | Sign in to Employee Account
114 | Tasks | Done